## Slide 1: Luis Muñoz Marín International Airport
AGC Transportation Conference
May 28, 2026

## Slide 2
2
1,438 Acres
Critical Infrastructure
Terminal A
8 Contact Gates
Terminal B
10 Contact Gates
Runway 8-26
10,400 x 193
SJU Airport
Terminal C
9 Contact Gates
Terminal D
3 Contact Gates
Runway 10-28
8,016 x 150

## Slide 3: SJU Historical Passenger Movement
Chart: 
| 1990 | 1991 | 1992 | 1993 | 1994 | 1995 | 1996 | 1997 | 1998 | 1999 | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025
Annual | 8.1679 | 8.0017 | 8.7831 | 8.948 | 9.4558 | 9.4263 | 9.5824 | 9.877 | 9.352 | 9.6861 | 10.308 | 9.5596 | 9.3728 | 9.1839 | 10.2407 | 10.4685 | 10.2884 | 10.1693 | 9.1621 | 8.2459 | 8.5671 | 7.9934 | 8.4482 | 8.346 | 8.6004 | 8.7374 | 9.0326 | 8.4074 | 8.3737 | 9.4483 | 4.8454 | 9.6842 | 10.311 | 12.1976 | 13.2474 | 13.6437

## Slide 4
SJU Passenger Movement
Chart: 2022 Supplemental
| PAL 1 (2028) | PAL 2 (2033) | PAL 3 (2043) | PAL 4 (2053)
Series 1 | 11.3 | 12 | 13.7 | 15.5
Chart: 2019 Master Plan
| PAL 1 (2021) | PAL 2 (2026) | PAL 2 (2036)
Series 1 | 11.3 | 12 | 13.6
Chart: 2026-2030 Forecast
| 2026 | 2027 | 2028 | 2029 | 2030
Series 1 | 13.9 | 14.4 | 14.8 | 15.1 | 15.5
23-YEAR offset
13.6M
2025 Annual Passengers

## Slide 5
5
c
2025
2030
2040
2035
2045
2050
Phase 1
Phase 2
Phase 3 Alternate
Phase 4
Baseline
Gates
Total SF*
TSA Lanes
USDA Lanes
+2
+308k
+4
+2
+203k
+4
+3
+187k
+1
Components
Development Timeframe
Combined All-
Terminal Peak Hour
4,485
5,152
5,479
5,790
+15%
+6%
+6%
+7
+698k
+4
+5
Total
Terminal Rehabilitation & Improvement Program (TRIP)

## Slide 6
t
6
Terminal Rehabilitation & Improvement Program (TRIP)
Passenger Capacity Improvements:
4 New additional USDA positions
Relocation of Check-In Positions to Terminal D
2 New contact gates
Expansion of International Baggage Claim in Terminal D FIS
5 new additional restrooms
Additional 19,000 SF of post-security concessions
Second Level
Gates
Total SF*
TSA Lanes
USDA Lanes
+2
+308k
+4
Phase 1
2025-2029
Infrastructure Improvements:
Interconnection Terminal A and Terminal B/C Baggage Handling Systems
Baggage Handling Expansion to Terminal D
Terminal D Chiller Plant, including replacement of chilled water mains and branch piping.

## Slide 7
7
32 New Boarding Bridges
+2 Additional Gates by 2031
Terminal A
8 Contact Gates
Terminal B
10 Contact Gates
PBB’s
Terminal C
9 Contact Gates
Terminal D
3 Contact Gates
$67.4M
Total Project Cost

## Slide 8
Multilevel Parking Expansion

## Slide 9
Multilevel Parking Expansion
OCTOBER
Schematic Design Submittal
Design Workshops
DECEMBER
70% CDs Issuance
APRIL
90% CD’s Issuance
Infrastructure Government Agencies Endorsement Submitted
JULY
Award Date
OCTOBER
Notice to Proceed 1
2026
RFP Stage 1
(Statement of Qualifications sent)
NOVEMBER
MARCH
GMP Cost Proposal Delivery
RFP Stage 2 (Additional Information sent to Qualified GC)
Pre-Bid Meeting
JANUARY
2025
2030
Design
Procurement
Construction
Project Timeline
JUNE
Contractor Selection
2026
JAN
Project Completion
JUNE
100% CDs Issuance
Construction Permit Submission

## Slide 10
10
Airport Pavement Managment System
SJU APMS
16.2 million
sqft of airfield pavement
Every 5 years
Notes: Aerostar manages approximately 16.2 million square feet of airfield pavement at Luis Muñoz Marín International Airport (SJU) and maintains an Airport Pavement Management System (APMS) in accordance with FAA requirements.
This system supports federal funding eligibility and serves as a key tool for planning and prioritizing pavement-related investments within Aerostar’s Capital Improvement Program (CIP).
Since the last APMS update in 2020, several major rehabilitation projects have been completed or are ongoing, and pavement conditions have evolved. This project focuses on updating the APMS with current data and analysis to ensure it remains an effective, reliable decision-making tool.
The effort includes comprehensive data collection, pavement condition assessments (PCI surveys), supplemental testing, traffic and fleet mix evaluation, and updated remaining life and Pavement Classification Rating (PCR) analyses. The project will ultimately deliver a prioritized Maintenance and Rehabilitation Plan with 5-, 10-, and 20-year projections, supported by updated mapping and reporting to guide future planning and investment decisions.-

## Slide 11: FAA Airport Capital Improvement Program FY 27-31
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
11
FY 26
(Ph3 Construction)
FY 27-28
(Design/Construction)
FY 28
(Construction)
FY 29-32
(Construction)
FY 31
(Design)
FY 29
(Design)
FY 28
(Ph1 Design)
FY 29
(Ph2 Construction)
FY 26
(APMS)
(AEIMP)
FY 29
(Design)
FY 29
(Design)
Airport Pavement Management System (2026)
Airport Electrical Infrastructure Master Plan (2026)
Runway 8-26 Object Free Area ROFA Clearing Ph3 Construction (2026)
Taxiway Sierra WEST Improvements Construction (2027)
Taxiway Sierra EAST Improvements Construction (2027)
Runway Safety Area Improvements Runway 10-28 Design (2028)
Taxiway H3-H4 Pavement Reconstruction Ph2 Construction (2028)
Airport Sustainability Project Design (2028)
Taxiway N2 Pavement Reconstruction (2028 & 2032)
Apron 3 Pavement Reconstruction (2029 & 2031)
Runway Safety Area Improvements Runway 10-28 Construction (2029)
Apron 6 Pavement Reconstruction Ph 1 Design (2029)
Taxiway J7 Geometrical Improvements Design (2029)
Taxiway J7 Geometrical Improvements Construction (2030)
Airport Sustainability Project Ph2 Construction (2030)
Apron 2 Pavement Reconstruction Ph 1 Design (2031)
FY 27-28
(Design/Construction)
FY2027
FY2028
FY2029
FY2030
$65.96M
$12.56M
$15.93M
$22.68M
FY2031
$15.18M
1
2
3
4
5
6
7
FY 28
(Ph1 Design)
8
9
10
11
12
13
FY 30
(Construction)
14
8
8
8
8
FY 30
(Ph2 Construction)
15
16

## Slide 12
Restrooms Rehabilitation Program
Expected Total Investment
$7.7M
Impacted Cluster Restrooms
3
Upcoming Cluster Restrooms
11

## Slide 13: Energy & Resiliency Projects
13
Power Generation Plant
Project Timing: 2021-2030
Funding Program: 100% FEMA Funded
$132M
Based on 60% design
Project Overview
Purpose: Ensures airport operational continuity during grid disruptions and catastrophic events
Oversight: Shared among FEMA, COR3, PRPA, and Aerostar
Confirmed Items
Project eligibility validated within FEMA/COR3/PRPA pathways
Phase 1A completed; Phase 1B design deliverables advanced to 60%
Design deliverables support scope definition and baseline planning
Aligned with FEMA resiliency objectives and mitigation strategy
Power generator equipment purchase was approved by FEMA on April 27, 2026
Pending Authorization
Amendment to complete the construction drawings up to a 90%
FEMA and COR3 authorization for Phase 2 construction
Confirmation of construction sequencing and funding release timing

## Slide 14: Capital Projects Expenditure Milestones
Chart: 
| Main Drivers | Others
 | 48.9 | 8.1
Restroom Rehab Prog
PBB’s Replacement
Multilevel Parking Lobbies
Parking Design and Construction
Roof Upgrade Plan
Commercial (Stores and Parking System Improvements)
Baggage Claim B/C Rehab
Terminal D Rehab Ph2
Inner Traffic Lane Phase 2
FIS Hallway Reconstruction
TWY N1 Const
ROFA
Taxiway S - Design
Main Drivers
$48.9M
Security Infrastructure
Real Estate
IT (Equipment Purchasing)
$57M
2026

## Slide 15: Luis Faure Bosch, MEM, PE, CM Chief Infrastructure Officer Luis Muñoz Marín International Airport
Thank you
AGC Transportation Conference